## Project Timeline
FINAL YEAR PROJECT TIMELINE
PHASE | DETAILS | Q2 | [12 empty] | DISSERTATION DEADLINE
|  | JAN |  |  |  | FEB |  |  |  | MAR
|  | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29
(Stage 2) Web Application Devlopment | Front-End and Back-end Setup (Basic) | JAN 4: EXAMS
Database Setup | bar: JAN 11
Login & Register (Authentication) | bar: JAN 18
Dashboard | bar: JAN 18
Usabilty Test Creation | bar: JAN 18 to JAN 25
(Stage 3) Local & Web Application Devlopment | Task and Question Displaying in Local App | bar: JAN 25
FER Model Integration & System Integration | bar: FEB 1
Screen Recording For Local Application | bar: FEB 1
Task and Question Displaying in Local App | bar: FEB 1
Video Uploading | bar: FEB 1
Display Data Web Application (Overview) | bar: FEB 8
Display Data Web Application (Recordings) | bar: FEB 15 to FEB 22
System Polishing | bar: MAR 1 to MAR 8
Deployment | bar: MAR 8
System Testing & Evaluation | bar: MAR 15 to MAR 22
Dissertation | Development | bar: MAR 15
FER Model | bar: MAR 22
System Testing and Evaluation | bar: MAR 22 to MAR 29
Future Work | bar: MAR 29