## Project Timeline
FINAL YEAR PROJECT TIMELINE
|  | START DATE | [6 empty] | 2020-12-10
PHASE | DETAILS | Q1 | [14 empty] | Q2 | [12 empty] | DISSERTATION DEADLINE
|  | SEP |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR
|  | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29
|  | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13
Resarch | General Machine Learning Research | DEC 14 WK 13: INTERIM REPORT DEADLINE |  |  | EXAMS
Background Research | bar: OCT 5 WK 3 to OCT 12 WK 4
Resarch Facial Expression Recognition | bar: OCT 12 WK 4 to NOV 2 WK 7
Dataset Rearch | bar: OCT 12 WK 4 to OCT 19 WK 5; NOV 9 WK 8
Technologies Research | bar: OCT 26 WK 6 to NOV 9 WK 8
Design | bar: NOV 9 WK 8 to NOV 30 WK 11
(Stage 1) FER Development | Dataset Selection and Preperation | bar: NOV 16 WK 9
Model Selection, Building and Training | bar: NOV 23 WK 10 to DEC 7 WK 12
Evaluation with Metrics | bar: DEC 7 WK 12
Input From Camera and Export Data | bar: DEC 7 WK 12
(Stage 2) Web Application Devlopment | Front-End and Back-end Setup (Basic)
Database Setup
Login & Basic Usabilty Test Creation
Local Python Application Starting Screen
FER Model Integration & System Integration
(Stage 3) Local & Web Application Devlopment | Screen Recording For Local Application
Task and Question Displaying in Local App
Video Uploading
Additonal Usability Test Creation Options
Display Data On Web Application
Embed Video on Website
System Integration
System Evaluation (Includes Real User)
Dissertation | New Literature
System Development
System Testing and Evaluation