## Project Timeline
FINAL YEAR PROJECT TIMELINE
|  | START DATE | [6 empty] | 2020-12-10
PHASE | DETAILS | Q1 | [14 empty] | Q2
|  | SEP |  | OCT |  |  |  | NOV |  |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APRIL
|  | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
|  | WK 1 | WK 2 | WK 3 | WK 4 | WK 5 | WK 6 | WK 7 | WK 8 | WK 9 | WK 10 | WK 11 | WK 12 | WK 13
Resarch | Research Machine Learning | bar: SEP 21 WK 1 to OCT 12 WK 4; NOV 2 WK 7
Resarch Facial Expression Recognition (FER) | bar: OCT 5 WK 3 to OCT 19 WK 5; NOV 2 WK 7
Research Usability Testing | bar: OCT 5 WK 3 to OCT 26 WK 6
Research Datasets | bar: OCT 5 WK 3
Research Architecture | bar: OCT 12 WK 4 to OCT 26 WK 6
Research Programming Languges | bar: OCT 19 WK 5 to OCT 26 WK 6
Research Emotions in Usability Testing
Research Existing Solutions (Usbaility Testing) | bar: OCT 19 WK 5 to NOV 2 WK 7
Initial Development | Research Design Methodology
Use Case Diagrams | bar: SEP 28 WK 2; OCT 19 WK 5 to OCT 26 WK 6
Get Existing Solutions to Work | bar: NOV 2 WK 7
Design the Facial Recgonition Architecture (High Level)
Design the Usability Testing Architecture (High Level)
Implement (FER)
Implement Basic Usability Testing
Final Devlopment